## DRAFT 2024 AAP
NANUMBA SOUTH DISTRICT COMPOSITE ANNUAL WORK PLAN AND BUDGET FOR 2024
PROGRAMME (PBB) |  | SUB-PROGRAMME (PBB) | BROAD ACTIVITY | LOCATION | TIME FRAME (2023) |  |  |  | COST (SOURCE OF FUNDING) |  |  |  |  | PROGRAMME STATUS |  | IMPLEMENT INSTITUTION/DEPARTMENT
[5 empty] | Q1 | Q2 | Q3 | Q4 | GoG |  |  | IGF | OTHERS | NEW | ON-GOING | LEAD | COLLABORATING
[9 empty] | DACF-RFG | GoG | DACF
MANDATORY ALLOCATION
1 | MANAGEMENT AND ADMINISTRATION | PLANNING, BUDGETTING AND COORDINATION | Support for the Sub-District Structures (2% of DACF) | Wulensi, Nakpayili and Chichagi | [6 empty] | 52556.07 |  |  | * |  | DA | MoLGDRD
2 | INFRASTRUCTURE DELIVERY AND MANAGEMENT | INFRASTRUCTURE DEVELOPMENT | Provide support for community initiated projects (5% DACF) | Selected Communities | [6 empty] | 200300 |  |  | * |  | DA | CDSW
Sub-total | [10 empty] | 252856.07
3 | ECONOMIC DEVELOPMENT | AGRICULTURE DEVELOPMENT | Re-vegetate degraded land with Cashew at Pudua | Pudua | [8 empty] | 420770.2 |  | * | DA | GPSNP II
4 |  |  | Maintain and nurture 1No degraded lands with Cashew Plantation | Tampoaya | [8 empty] | 8000 |  | * | DA | GPSNP II
5 |  |  | Rehabilitate Small Earth Dam at Sakpe | Sakpe | [8 empty] | 586072.89 | * |  | DA | GPSNP II/GIDA
6 |  |  | Rehabilitate Small Earth Dam at Lungni | Lungni | [8 empty] | 586072.89 | * |  | DA | GPSNP II/GIDA
7 |  |  | Rehabilitate Kotoya-Wajuldo-Madado feeder road | Kotoya-Wajuldo-Madado | [8 empty] | 560641.8 | * |  | DA | GPSNP II/DFR
8 |  |  | Construct Parallell Drain at Wulensi Small Earth Dam | Wulensi | [8 empty] | 358323.83 |  | * | DA | GPSNP II/GIDA
Sub-total | [12 empty] | 2519881.61
DEPARTMENT OF AGRICULTURE
9 | ECONOMIC DEVELOPMENT | AGRICULTURE DEVELOPMENT | Internal management of the department (Stationeries, Utilities and maintenance of office equipment) | Wulensi | [5 empty] | 5000 |  | 3064 | 2800 |  | * | DA | DADU
10 |  |  | Procurement of vehicles tyres, vehicle insuarance, road worthiness, maimtenance of official vehicles and motor bikes | DAD - Wulensi | [5 empty] | 11000 | 10000 | 8000 | 2850 |  | * | DA | DADU
11 |  |  | Procurement of 1No. Laptop computer | DAD - Wulensi | [7 empty] | 5000 |  | * |  | DA | DADU
12 |  |  | Supprt on the job training of staff of the department (TEDMAG, review meetings etc,) | DAD - Wulensi | [5 empty] | 6500 | 5000 |  |  |  | * | DA | DADU
13 |  |  | Carry out extension service delivery on farmer empowerment activities for 28,650 farmers and conduct disease surveillence on crops and livestock (ie FAW, PPR, CBPP, NCD, Rabies etc). | District-Wide | [5 empty] | 5500 |  |  | 48000 |  | * | DA | DADU
14 |  |  | Conduct supervision and monitoring visits on activity implementation on the field | District-Wide | [6 empty] | 4600 |  | 47000 |  | * | DA | DADU/DPs
15 |  |  | Targeting to form 25 Farmer Based Organization (FBOs) and link them to department of cooperative or District Assembly for registration | District-Wide | [5 empty] | 4600 | 3200 |  |  |  | * | DADU | DOC
16 |  |  | Conduct Zonal and District Research and Extension Linkage Committee meetings for 120 and 50 Agric Value Chain actors | Wulensi, Lungni, Nakpayili and Kukuo | [5 empty] | 3200 | 3600 |  |  |  | * | DADU | RAD
17 |  |  | Educate 180 farmers from 6FBOs on pest and disease management | Wulensi, Gbungbaliga, Kpansu, Moba, Ponayili and Kanjo | [5 empty] | 500 |  |  | 820 | * |  | DA | DAD/DPs
18 |  |  | Establish crop demonstration on conservation agricultural practice and varietal trial in 3 communities each. | Monyindo, Baduli, Tampuaya, Pudua, Garikpe and Tambihini | [5 empty] | 5500 |  |  | 5000 |  | * | DA | DAD/DPs
19 |  |  | Train 9750 farmers on climate smart agriculture and use of agro chemiclas | District-Wide | [7 empty] | 10000 | 8500 |  | * | DA | DAD/DPs
20 |  |  | Educate 550 farmers on agro ecological farming system | Selected communities | [5 empty] | 2000 |  |  | 1500 | * |  | DA | DAD/DPs
21 |  |  | Educate 20 tractor operators on appropraite land preparation | Selected communities | [5 empty] | 1500 |  |  | 2000 | * |  | DA | DAD/DPs
22 |  |  | Carry out Prophylatic treatment of livestock and sensitization of farmers on the need to patronize veterinary services | District-Wide | [5 empty] | 2300 |  |  | 2200 |  | * | DA | DAD/DPs
23 |  |  | Educate 700 farmers on causes, management of aflatoxin and prevention of post harvest losses | Kpayansi, kotoya,Tinigeria,Chifilni,Sakpe,Nassamba,Bandiyili,Pudua,Egambo and Gbungbaliga | [5 empty] | 2000 |  |  | 2000 |  | * | DA | DAD/DPs
24 |  |  | Educate 28,000 farmers on the effects of climate change on livestock feed and management of feed and water resources | District-Wide | [5 empty] | 2500 |  |  | 6000 | * |  | DA | DAD/DPs
25 |  |  | Sensitize 300 farmers on livestock FBOs formation | Maggiedo,Chando,Bandajua,Nabayili,Bienayili,Juali,Kajeso,Gimam,Lankani and Lahito. | [5 empty] | 400 |  |  | 1200 |  | * | DA | DAD/DPs
26 |  |  | Educate 200 farmers on value chain in livestock production | Wulensi,Chichagi,Gmalpedo and Opijua | [8 empty] | 600 | * |  | DA | DAD/DPs
27 |  |  | vaccinate 4,600 cattle against CBPP | District Wide | [5 empty] | 1500 |  |  | 2000 |  | * | DA | DAD/DPs
28 |  |  | Vaccinate 3,500 sheep and goat against PPR | District Wide | [5 empty] | 2000 |  |  | 1500 |  | * |  | DAD/DPs
29 |  |  | Vaccinate 3,800 local poultry against NCD | District-Wide | [5 empty] | 1500 |  |  | 1500 |  | * | DA | DAD/DPs
30 |  |  | Meat inspection and issuance of slaughter and movement permit | District Wide | [5 empty] | 1200 |  |  | 1300 |  | * | DA | DAD/DPs
31 |  |  | Support the Linkage of agric value chain actors | District Wide | [5 empty] | 2000 |  |  | 4000 |  | * | DA | DAD/DPs
32 |  |  | Support National Farmers day celebration | Selected Community | [7 empty] | 60000 |  |  | * | DA | DAD/DPs
33 |  |  | Sensitize 2,600 farmers on the dangers of rabies | District Wide | [8 empty] | 2400 |  | * | DA | DAD/DPs
34 |  |  | Train 60 women gari processors on value addition in 3 communities | Kajeso,Kpayansi and Tampoya | [5 empty] | 1500 |  |  | 3000 | * |  | DA | DAD/DPs
35 |  |  | Educate 120 women farmers on backyard gardening and nutrient conservation in food preparation | Wulensi,Zonyohini,Nassamba,Baduli | [5 empty] | 1350 |  |  | 1200 |  | * | DA | DAD/DPs
36 |  |  | Educate 120 women farmers on food safety (food, water personal and environmental hygeige | Wulensi,Tokrodo,ponayili,Gbedeke | [5 empty] | 1350 |  |  | 1200 | * |  | DA | DAD/DPs
37 |  |  | Educate 30 women farmers on off farm house livelihood activities(soap making and soya khebab) | Wulensi | [5 empty] | 3500 |  |  | 3500 | * |  | DA | DAD/DPs
38 |  |  | Educate 80 women shea pickers on safety measures, proper parboiling and drying of shea nut | Gbungbaliga,Binda | [5 empty] | 2000 |  |  | 2500 |  | * | DA | DAD/DPs
39 |  |  | Support the maintaitenance of the district centre for Agriculture commence and technology (DCACT) | Districts Wide | [5 empty] | 3000 |  | 2500 | 3000 |  | * | DA | DAD/DPs
40 |  |  | Conduct weekly market survey on commodity prices | Wulensi,Lungni, and Nakpayili markets | [5 empty] | 2000 |  | 1000 | 2000 |  | * | DA | DAD/DPs
41 |  |  | Support the implementation of government flagship project(PERD,IVID PFJ Etc) | District Wide | [10 empty] | * | DA | DAD/DPs
42 |  |  | Air 12 radio episodes to educate farmers on agricultural activities | District Wide | [5 empty] | 2400 |  | 3000 | 3000 | * |  | DA | DAD/DPs
43 |  |  | Conduct Listening of farm households, field measurement and establishment of yield plots in 20 communities | Selected commuities | [5 empty] | 4000 |  |  | 5000 |  | * | DA | DAD/DPs
Sub-total | [9 empty] | 81800 | 26400 | 92564 | 167570
HEALTH
44 | SOCIAL SERVICES DELIVERY | HEALTH DELIVERY | Implement HIV/AIDs activities | District-Wide | [6 empty] | 18929.32 |  |  |  | * | DA | AIDS COMMISSION
45 |  |  | Support in the internal runs of the District health Directorate | District-Wide | [6 empty] | 10000 |  |  |  | * | DA | GHS
46 |  |  | Complete the construction of 1No CHPS compound at Gunguni | Gunguni | [6 empty] | 110169.08 |  |  |  | * | DA | GHS
47 |  |  | Conduct sensitization on the importance of growth monitoring and promotions through durbars and radio discussion | District-Wide | [5 empty] | 10000 |  |  |  |  | * | DNO | DHMT
48 |  |  | Ensure all pregnant women are put on IFA supplementation using the safe motherhood protocols and promote the consumption of Iron Rich Diversified foods | District-Wide | [8 empty] | 4000 |  | * | DNO | DHMT
49 |  |  | Sensitize community members on exclusive breast feeding (EBF) | District-Wide | [7 empty] | 4000 |  |  | * | DNO | DHMT
50 |  |  | Collaborate with DA and GES to carry out diet quality checks on the food cooked for the pupils every term | District-Wide | [5 empty] | 3000 |  |  |  |  | * | DNO | DHMT
51 |  |  | Embark on monthly monitoring of facilities on Vit A distribution and intensify Schools distribution of Vit A caps to eligible childrentwice in a year | District-Wide | [7 empty] | 5000 |  |  | * | DNO | DHMT
52 |  |  | Conduct cooking demonstrations using locally available foods | District-Wide | [8 empty] | 6000 |  | * | DNO | DHMT
53 |  |  | Provide regular targated counseling for all pregnant women and vulnerable children by increasing the number of C-IYCF counseling home visits | District-Wide | [8 empty] | 4000 |  | * | DNO | DHMT
54 |  |  | Support School health teachers to give all in School adolescent girls weekly dos of IFA tablets | All School adolescent girls | [8 empty] | 4000 |  | * | DNO | DHMT
55 |  |  | Intensify Out of School adolescent IFA supplementation | District-Wide | [8 empty] | 4000 |  | * | DNO | DHMT
56 |  |  | NID support, monitoring durbars, malaria control, advocacy on COVID-19 etc. | District-Wide | [6 empty] | 20000 | 3000 | 50000 |  | * | DA | GHS/CSOs
57 |  |  | Conduct health educational session on the importance of family planning, Skilled delivery and early ANC. | District-Wide | [6 empty] | 8000 | 2000 | 2000 |  | * | DA | GHS/CSOs
58 |  |  | Support the District Health Directorate for the procurement of Anti snake Venom | District-Wide | [6 empty] | 14639.72 |  |  |  | * | MP | GHS
59 |  |  | Payment of Retension of 1No. OPD Block at Wulensi Hospital | Wulensi |  |  |  |  | 14869.35 | [5 empty] | * | DA | GHS
60 |  |  | Organise Public campaigns to sensitize people on migration and health issues | District-Wide | [6 empty] | 10000 | 2000 | 8000 |  | * | DA | GHS/CSOs
Sub-total | [8 empty] | 14839.35 | 13000 | 191738.12 | 10000 | 66000
EDUCATION & SPORTS
61 | SOCIAL SERVICES DELIVERY | EDUCATION AND YOUTH DEVELOPMENT | Supply of 1000No. Fabricated Metal dual Desk to District Education Directorate for distribution to basic Schools | District Education Office-Wulensi | [5 empty] | 250000 | 50000 |  |  | * |  | DA | GES
62 |  |  | Conduct Comprehensive school inspection in 20 selected schools | District-Wide | [8 empty] | 100000 | * |  | DA | GES
63 |  |  | Complete the construction of 1No 3-Unit Classroom block at Wanguldo | Wanguldo | [6 empty] | 114410.92 |  |  |  | * | DA | GES
64 |  |  | Conduct monitoring on the conduct of Professional Learning Community (PLC) in all schools | District-Wide | [6 empty] | 25000 |  |  |  | * | DA | GES
65 |  |  | Support for my first day at School | District-Wide | [6 empty] | 30000 |  |  |  | * | DA | GES
66 |  |  | Support for the needy but brilliant students | District-Wide | [6 empty] | 92556.07 |  |  |  | * | DA | GES
67 |  |  | Complete the Constructiong and furnishing of 1No. 3-unit classroom block with ancillary facilities at Gimam JHS (Retension) | Gimam |  |  |  |  | 51348.57 | [5 empty] | * | DA | GES
68 |  |  | Complete the payment for the rehabilitation of 3No. 3-units classroom blocks (Retension) | Chichagi, Zoyohini & Tinageria |  |  |  |  | 8835.25 | [5 empty] | * | DA | GES
69 |  |  | Organize quarterly DEOC meetings | Wulensi | [6 empty] | 3800 |  |  |  | * | DA | GES
70 |  |  | Organize Inter-circuit and Inter-District Sports Competition | District-Wide | [6 empty] | 15000 |  |  |  | * | DA | GES
71 |  |  | Suppor Complementary Education Agency (CEA) in the district to implement its activities | District-Wide | [6 empty] | 8000 |  | 4000 |  | * | CEA | GES
72 |  |  | Organize district wide mock exams for all JHS final year students | District-Wide | [6 empty] | 8000 |  |  | * |  | GES | DA
73 |  |  | Organize Inter-District Cultural activities | District-Wide | [5 empty] | 5000 | 5000 |  |  | * |  | CNC | GES
74 |  |  | Sensitize communities on the need for Parents to Send their Children to School at the right Age | District-Wide | [5 empty] | 20000 |  |  |  | * |  | GES | DA
75 |  |  | Sensitize Parent to Support their wards with basic School needs | Diastrict-wide | [5 empty] | 3000 | 2000 |  |  | * |  | GES | DA
76 |  |  | Renovate the Office of the District Education Directorate | Wulensi | [6 empty] | 35000 |  |  | * |  | DA | GES
77 |  |  | Conduct Annual Monitoring and inspection of schools | District-Wide | [5 empty] | 2000 | 1500 |  |  |  | * | GES | DA
78 |  |  | Conduct staff rationalization and posting of new trained teachers | District-Wide | [5 empty] | 1500 | 1000 |  |  |  | * | GES | DA
79 |  |  | Identify and award hard working teachers in the district | District-Wide | [5 empty] | 3000 | 5000 |  |  |  | * | DA | GES
80 |  |  | Train teachers on how to complete the Annual School Census forms | District-Wide | [5 empty] | 1500 | 2000 |  |  |  | * | GES | DA
81 |  |  | Monitor school feeding programme in the district | District-Wide | [6 empty] | 4000 |  |  |  | * | DA | GES/SHEP
82 |  |  | Train teachers on gender sensitive pedagogy | District-Wide | [5 empty] | 2000 | 4000 |  |  |  | * | GES/Girld Child Officer | DA
83 |  |  | Organize cluster level sensitization for school heads and health teachers on gender sensitivity | District-Wide | [5 empty] | 1200 | 2000 |  |  |  | * | GES/Girld Child Officer | DA
84 |  |  | Create and strengthen girls clubs in all the JHSs | District-Wide | [6 empty] | 3000 |  | 4000 |  | * | GES/Girld Child Officer | DA
85 |  |  | Conduct auditing in all the schools on CAPITATION / GALOP accounts | District-Wide | [8 empty] | 6000 |  | * | GES | DA
86 |  |  | Conduct payroll auditing at the district education | District-Wide | [5 empty] | 1200 | 1000 |  |  |  | * | GES | DA
87 |  |  | Conduct data verification in schools | District-Wide | [6 empty] | 1500 |  |  |  | * | GES | DA
88 |  |  | Train teachers on the use of ICT | District-Wide | [5 empty] | 2000 | 2000 |  |  |  | * | GES | DA
89 |  |  | Provide portable drinking water to schools | District-Wide | [6 empty] | 30000 |  | 62000 |  | * | DA | DPs
90 |  |  | Conduct data collection to track high and low performing schools in the district | District-Wide | [6 empty] | 4000 |  |  |  | * | GES | DA
91 |  |  | Organize Spam at all the circuits levels | District-Wide | [5 empty] | 2000 | 1500 |  | 5000 |  | * | GES | DA/CSOs
92 |  |  | Train Teachers on the use of the new standardized Curriculum | District-Wide | [5 empty] | 3000 | 5000 |  | 5000 |  | * | GES | DA/CSOs
93 |  |  | Rehabilitate dilapidated/Ripped off Schools | Selected Schools | [6 empty] | 150000 |  |  | * |  | DA | GES
94 |  |  | conduct monitoring to schools on the use of Play-Based Methods in teaching | Wulensi | [8 empty] | 18000 | * |  | Right-to-Play | GES
Sub-total | [8 empty] | 60183.82 | 297400 | 606266.99 |  | 5000
ENVIRONMENT, WATER AND SANITATION
95 | ENVIRONMENTAL AND SANITATION MANAGEMENT | DISASTER PREVENTION AND MANAGEMENT | Carry out Evacuation of refuse dumps in the district | District-Wide | [6 empty] | 32000 |  |  |  | * | DEHU | DA
96 |  |  | Legislation and Enforcement of sanitation bye-Laws | District-Wide | [6 empty] | 13500 |  |  |  | * | DEHU | DA
97 |  |  | Dislodgement of Public Toilets in the District | District-Wide | [6 empty] | 32000 |  |  |  | * | DEHU | DA
98 |  |  | Monthly Sanitation Day /Clean Up exercise | District-Wide | [6 empty] | 15000 |  |  |  | * | DEHU | DA
99 |  |  | Conduct Medically Screening on food venders | District-Wide | [6 empty] | 10000 |  |  | * |  | DEHU | DA
100 |  |  | Sensitize water vendors to ensure that they keep the stand pipes clean and safe for consumption | Wulensi, Lungni & Nakpayili | [6 empty] | 6000 |  |  | * |  | DEHU | DA
101 |  |  | Carry out Field activities monitoring | District-Wide | [6 empty] | 5000 |  |  |  | * | DEHU | DA
102 |  |  | Conduct CLTS Activities | District-Wide | [6 empty] | 8000 |  | 12000 |  | * | DEHU | DPs
103 |  |  | Repair of motorbikes | [7 empty] | 10000 |  |  |  | * | DEHU | DA
104 |  |  | Procurement of sanitary tools and PPEs | [7 empty] | 10000 |  |  |  | * | DEHU | DA
105 |  |  | Carry out ESICOME Activities | District-Wide | [7 empty] | 5000 |  | * |  | DEHU | DA
106 |  |  | Watsan mapping & Rehabilitation of broken Boreholes | District-Wide | [6 empty] | 20000 |  |  | * |  | DEHU | DA
107 |  |  | Pro-poor Latrine support | District-Wide | [6 empty] | 12000 |  |  | * |  | DEHU | DA
108 |  |  | Preparation of DESSAP | District-Wide | [6 empty] | 15000 |  |  | * |  | DEHU | DA
109 |  |  | Disinfection and Disinfestation | District-Wide | [6 empty] | 9000 |  |  |  | * | DEHU | DA
110 |  |  | Service provider activities monitoring | District-Wide | [6 empty] | 12000 |  |  |  | * | DEHU | DA
111 |  |  | Conduct Nutrition Orientation for food vendors and School feeding program contractors | District-Wide | [6 empty] | 8000 |  |  | * |  | DEHU | Nutrition Officer
112 |  |  | Collaborate with SAHA GLOBAL to provide cleanest water to 9 poorest communities | Akonsiya, Gbandi, Gbedeke, Kambo 2, Kwame krom 1&2, Chaginaaya 2, Napado etc | [8 empty] | 10000 | * |  | SAHA GLOBAL | DA
113 |  |  | Construct 2No. Urinals at the Wulensi Nakpayili and Lungni market | Wulensi and Lungni | [7 empty] | 22800 |  | * |  | DA | DPCU
Sub-total | [10 empty] | 217500 | 27800 | 22000
CENTRAL ADMINISTRATION
114 | MANAGEMENT AND ADMINISTRATION | PLANNING, BUDGETTING AND COORDINATION | Conduct community Durbars/Engagements in the district | District-Wide | [6 empty] | 18000 |  |  |  | * | DA | DPCU
115 |  |  | Conduct Town Hall meetings on the implementation of Annual Budget and Work Plans | Wulensi | [6 empty] | 15000 |  |  | * |  | DA | DCPU
116 |  |  | Conduct Reviews on the preparation of Annual Work Plans and Budget | Wulensi | [6 empty] | 12000 |  |  | * |  | DPCU | DA
117 |  |  | Service meetings of statutory committees of the Assembly | Wulensi | [6 empty] | 35000 |  |  |  | * | DA | DPCU
118 |  |  | Service Quarterly DPCU & Budget Committee meetings | Wulensi | [6 empty] | 12000 |  |  |  | * | DA | DPCU
119 | MANAGEMENT AND ADMINISTRATION | GENERAL ADMINISTRATION | Carry out Sensitization and Social Acountabilty Forum on LIPW beneficiary communities | Beneficiary communities | [8 empty] | 12000 | * |  | DA | Donor Partners
120 |  |  | Internal management of the organization | Wulensi | [6 empty] | 1320000 |  |  |  | * | DA | DPCU
121 |  |  | Support for the cellebration of national events | District-Wide | [6 empty] | 80000 |  |  |  | * | DA | DPCU
122 |  |  | Hosting official guest (refreshment, accomodation, fuel, donations etc) | Wulensi | [6 empty] | 100000 |  |  |  | * | DA | DPCU
123 |  |  | Service activities of the District Entity Tender Committee | Wulensi | [6 empty] | 8000 |  |  |  | * | DA | DPCU
124 |  |  | Support the activities of Birth and Death registry Department | District-Wide | [6 empty] | 25000 |  |  |  | * | B&D | DPCU
125 |  | PLANNING, BUDGETTING AND COORDINATION | Conduct quarterly Monitoring & Evaluation of Programmes & Projects of the Assembly | District-Wide | [6 empty] | 32000 |  |  |  | * | DA | DPCU
126 |  | GENERAL ADMINISTRATION | Sensitize Public and Implement NACAP, PFM act & Social Acountability | District-Wide | [6 empty] | 12000 |  |  |  | * | CHRAJ & NCCE | DPCU/DPs
127 | INFRASTRUCTURE DELIVERY AND MANAGEMENT | INFRASTRUCTURE DEVELOPMENT | Construct and Furnish 1No. District Fire Service Office at Wulensi | Wulensi |  |  |  |  | 348925 |  |  |  |  | * |  | DA | DPCU
128 |  |  | Construct and Furnish 1No. 4-Units Office Space with Ancillary facilities for some decentralized departments | Wulensi |  |  |  |  | 228420 |  |  |  |  | * |  | DA | DPCU
129 |  |  | Complete the construction of the District Assembly Stores | Wulensi | [6 empty] | 71101.03 |  |  |  | * | DA | DWD
130 | MANAGEMENT AND ADMINISTRATION | HUMAN RESOURCE MANAGEMENT | Support capacity building of staff of the Assembly and decentralized departments | Wulensi | [6 empty] | 58000 |  |  |  | * | DA | DPCU
131 | MANAGEMENT AND ADMINISTRATION | GENERAL ADMINISTRATION | Procurement of office Supplies and Consumables | wulensi | [6 empty] | 60000 |  |  |  | * | DA | DPCU
132 |  |  | Service Audit Committee Meetings of the DA | Wulensi | [6 empty] | 20000 |  |  |  | * | DA | IA
133 | SOCIAL SERVICES DELIVERY | EDUCATION AND YOUTH DEVELOPMENT | Support for sports development | Wulensi | [6 empty] | 150000 |  |  | * |  | DA | DPCU
134 | MANAGEMENT AND ADMINISTRATION | GENERAL ADMINISTRATION | Disbursement of MPs Common Fund | Wulensi | [6 empty] | 50000 |  |  |  | * | MP | DA
135 |  |  | Support to Traditional Authority and Tourism related activities | District-Wide | [6 empty] | 60000 |  |  |  | * | DA | TA/CNC
136 |  | FINANCE AND REVENUE MOBILIZATION | Preparation and submission of monthly and annual financial statements | Wulensi | [6 empty] | 25000 |  |  |  | * | DA | DFO
137 | INFRASTRUCTURE DELIVERY AND MANAGEMENT | INFRASTRUCTURE DEVELOPMENT | Rehabiliate and furnish DPO and DWE Bunglows | Wulensi | [6 empty] | 90000 |  |  | * |  | DA | DWD
138 | MANAGEMENT AND ADMINISTRATION | HUMAN RESOURCE MANAGEMENT | Organize inservice training for Assembly Persons to build their capacity in local governance | Wulensi | [6 empty] | 20000 | 2000 |  | * |  | DA | MoLGDRD/PM
139 |  |  | Procurement of office equipment for staff | Wulensi | [6 empty] | 30000 |  |  | * |  | DA | DPCU
Sub-total | [8 empty] | 577345 |  | 2303101.03 | 2000 | 12000
SPATIAL PLANNING/ROADS
140 | INFRASTRUCTURE DELIVERY AND MANAGEMENT | PHYSICAL PLANNING AND DEVELOPMENT CONTROL | Organize Sensitization programmes on the importance of Spatial Planning | District-wide | [5 empty] | 10000 | 5000 |  |  |  | * | PPD | DA, DTSC/DSPC members
141 |  |  | Organize Quarterly SAT meetings to deliberate on ongoing Street Naming and Property Addressing | NSDA | [6 empty] | 25000 |  |  |  | * | PPD | DA/Traditional council
142 |  |  | Carry Quarterly SPC and TSC meetings to prepare SDF &SP; deliberate on permit applications | District-Wide | [6 empty] | 12000 |  |  |  | * | PPD | DA, SPC/TSC Members
143 |  | OFFICE EQUIPMENT/RETOOLING | Procure office Desk, Desk top, Laptop and Printer to facilitate permit processing and hosting of Geo-spatial data | PPD Office | [6 empty] | 25000 |  |  |  | * | PPD | DA
144 |  |  | Procure 1No. Motorbike to facilitate routine fieldwork | PPD Office | [6 empty] | 17000 |  |  |  | * | PPD | DA
145 |  |  | Extensition of street lights to communities along the major streets to enhance road lighting | District-Wide | [6 empty] | 25000 |  |  |  | * | DA | Dept. of feeder roads/Works Dept.
146 |  |  | Digitize all structures and roads in the Wulensi, Nakpayili & Lungni | Wulensi, Nakpayili and Lungni | [6 empty] | 7000 |  |  |  | * | PPD | DA
147 |  |  | Organise Ground-Truthing exercise for the District Capital town | Wulensi | [6 empty] | 20000 |  |  |  | * | PPD | DA
148 |  |  | Acquire and Install Street signage & Property plates | Nakpayili, Wulensi & Lungni |  |  |  |  | 20000 | 10000 | 5000 |  |  |  | * | PPD | Chiefs, Assembly Members
149 |  |  | Acquire a satellite image for Wulensi, Nakpayili and Lungni township | Wulensi, Nakpayili &Lungni | [6 empty] | 18000 |  |  |  | * | PPD | DA
150 |  |  | Support the clearing of road side vegetation to enhance visibility | Major Roads | [6 empty] | 5000 | 1000 |  |  | * | DA | Dept. of feeder roads/Works Dept.
151 |  |  | Support the preparation of structural plans for the district | District-Wide | [6 empty] | 20000 |  |  | * |  | PPO | DA
152 |  |  | Facilitate the construction of speed humps on the major streets to reduce speeding | Major Roads | [6 empty] | 40000 |  |  |  | * | DA | Dept. of feeder roads/Works Dept.
153 |  | INFRASTRUCTURE DEVELOPMENT | Rehabilitate existing feeder roads with Culverts within the district | District wide | [6 empty] | 300000 |  |  | * |  | DA | DWD
Sub-Total | [8 empty] | 20000 | 20000 | 524000 | 1000 | 218000
ECONOMIC DEVELOPMENT/BAC
154 | MANAGEMENT AND ADMINISTRATION | FINANCE AND REVENUE MOBILIZATION | Training of Second Batch of You Start Beneficiaries | Wulensi | [8 empty] | 25000 |  | * | GEA | BAC
155 |  |  | Sensitization on the needs to register for the business operating permit | Wulensi, Nakpayili and Lungni | [7 empty] | 2000 |  |  | * | BAC | DPCU
156 |  |  | Facilitate the need to register for Business Operating Permit | Wulensi | [7 empty] | 2000 |  |  | * | BAC | DPCU
157 |  |  | Financial Literacy Training on Grow Your Business | District-Wide | [8 empty] | 15000 |  | * | GEA | BAC
158 |  |  | Monitoring of Livelihood Empowerment Project | Aprusaya, Naamani & Nlendo | [8 empty] | 2500 |  | * | ActionAid | BAC
159 |  |  | Monitoring of YAW beneficiaries | District-Wide | [8 empty] | 5000 |  | * | CAMFED | BAC
160 |  |  | Procure electrical materials and extend electricity to newly developed areas (50No. 8m wooden poles, 8,000m 50mm cables, 200No. Complete D-Iron, 15No. Complete Stay) | Lungni, Nakpayili, Parts of Wulensi and Selected communities |  |  |  |  | 148925 |  | 250000 |  |  | * |  | DA | DPCU
161 | MANAGEMENT AND ADMINISTRATION | FINANCE AND REVENUE MOBILIZATION | Intensify Revenue Mobilization Awareness | District-Wide | [6 empty] | 5000 | 8000 |  |  | * | DA | MoTI
162 |  |  | Support the development of 1D1F & Yam market in the District | Wulensi | [6 empty] | 20000 |  |  |  | * | DA | DPCU
163 |  |  | Support the training of groups to enhance local economic activities | District-Wide | [6 empty] | 10000 |  |  |  | * | DA | BAC
164 |  |  | Construct Yam sheds at Binda Yam Market | Binda | [7 empty] | 28500 |  | * |  | DA | Binda community
Sub-total | [8 empty] | 148925 |  | 285000 | 40500 | 47500
THE VULNERABLE & EXCLUDED, COMMUNITY DEVELOPMENT AND SOCIAL WELFARE
165 |  |  | Monitor Leap Payment in selected communities | District-Wide | [5 empty] | 15600 |  | 6000 |  |  | * | CDSW | DA
166 |  |  | Establish Child Protection Teams in 10 Communities | District-Wide | [5 empty] | 3900 |  | 4300 |  | * |  | CDSW | DA
167 |  |  | Disbursement of economic relief items to persons with Disabilities (PWDs) | District-Wide | [5 empty] | 243200 |  |  |  |  | * | CDSW | DA
168 |  |  | Engage Persons with Disabilities in skills training | Selected communities | [5 empty] | 4200 |  | 19800 |  |  | * | CDSW | DA
169 |  |  | Monitoring visit to early childhood development centres in the District. | 5 selected Schools | [5 empty] | 7790 |  | 410000 |  | * |  | CDSW | DA
170 |  |  | Engage vulnerable women and men in income generating activities and provision of startup capitals under the Productive Inclusion (PI) | Selected Communities | [7 empty] | 450000 |  |  | * | CDSW | DA
171 |  |  | Training of 8 communities on unpaid care works | Selected Communities | [5 empty] | 3200 |  | 2000 |  |  | * | CDSW | DA/CSOs
172 |  |  | Departmental Quarterly meeting | Wulensi | [5 empty] | 2200 |  |  |  |  | * | CDSW | DA
173 |  |  | Re-vamping of VSLA in 10 communities | Selected Communities | [5 empty] | 700 |  | 2800 |  |  | * | CDSW | DA/CSOs
Sub-total | [9 empty] | 280790 |  | 894900
GENDER ACTIVITIES
174 | SOCIAL SERVICES DELIVERY | SOCIAL WELFARE AND COMMUNITY DEVELOPMENT | Organize public education campaigns to sensitize institutions and the public to involve women in decision- making process | Lungni, Wulensi, Nakpayili and Gbungbaliga | [5 empty] | 1500 |  |  |  |  | * | GDO | DPCU
175 |  |  | Sensitize institutions, chiefs, landlords and opinion leaders to fairly allocate productive resources to empower women economically | Kanjo, Lankani, Kotoya & Binda | [5 empty] | 1000 |  |  | 3000 |  | * | GDO/SWCD | DPCU
176 |  |  | Engage Gender Model Families (GMFs) in alternative income generating activities with start-up equipment | Selected 5 communities | [8 empty] | 75000 |  | * | DCSW/GDO/BAC | DPs
177 |  |  | Identification of Gender Based Violence in some selected communities | Lungni, Wulensi, Kukuo & Kanjo Kura | [5 empty] | 1500 |  |  | 1000 |  | * | GDO/SWCD | DPCU
Sub-total | [9 empty] | 4000 | 0 |  | 79000
SECURITY
178 | MANAGEMENT AND ADMINISTRATION | GENERAL ADMINISTRATION | Provide support to security agencies within the district annually/DISECT meetings | Wulensi | [6 empty] | 150000 |  |  |  | * | DA | Ghana Police Service & others
179 | SOCIAL SERVICES DELIVERY | SOCIAL WELFARE AND COMMUNITY DEVELOPMENT | Organize community durbars on security awareness | District-Wide | [6 empty] | 10000 |  | 8000 |  | * | DA | DPCU
180 |  |  | Support the training of community members to co-exist with one another | District-Wide | [6 empty] | 12000 |  | 5000 |  | * | DA | DISECT
Sub-total | [10 empty] | 172000 |  | 13000
DISASTER MANAGEMENT AND EMERGENCY PREPAREDNESS
181 | ENVIRONMENTAL AND SANITATION MANAGEMENT | DISASTER PREVENTION AND MANAGEMENT | Organized educational campaign on planting trees to serve as windbreaks | District–wide | [6 empty] | 80000 |  |  | * |  | NADMO | DPCU
182 |  | NATURAL RESOURCE CONSERVATION | Organized communities’ sensitization in flood prone communities on early warning signs | Flood prone communities | [6 empty] | 11000 |  | 5000 | * |  | NADMO | DPCU
183 |  | DISASTER PREVENTION AND MANAGEMENT | Sensitization on poisoning of small water bodies for fishing | 12 Zones | [6 empty] | 8000 |  | 1200 | * |  | NADMO | DPCU/DPs
184 |  | NATURAL RESOURCE CONSERVATION | Organized sensitization meetings on the effects of wind/rain storms | District-Wide | [6 empty] | 16344 |  | 2000 | * |  | NADMO | DPCU
185 |  | DISASTER PREVENTION AND MANAGEMENT | Organized District Disaster Committee meeting | District-Wide | [6 empty] | 8000 |  | 4000 | * |  | NADMO | DPCU
186 |  | DISASTER PREVENTION AND MANAGEMENT | Organized educational campaign on environmental cleanliness | Wulensi | [6 empty] | 12000 |  |  | * |  | NADMO | DPCU
187 |  | DISASTER PREVENTION AND MANAGEMENT | Attend organized staff capacity building training | Tamale | [6 empty] | 20000 |  | 8000 |  | * | NADMO | DPCU
Sub-total | [10 empty] | 155344 |  | 20200
GRAND TOTAL (GH₵) | [8 empty] | 821293.17 | 663990 | 4677205.22 | 1068764 | 3170151.61

## GPSNPII
2023 DRAFT WORK PLAN AND BUDGET FOR NANUMBA SOUTH DISTRICT-GHANA PRODUCTIVE SAFETY NET PROJECT II (GPSNPII)
PROGRAMME (PBB) |  | SUB-PROGRAMME (PBB) | BROAD ACTIVITY | LOCATION | TIME FRAME (2023) |  |  |  | COST (GH₵) | PROGRAMME STATUS |  | IMPLEMENTING INSTITUTION/DEPARTMENT
[5 empty] | Q1 | Q2 | Q3 | Q4 | GPSNP II | NEW | ON-GOING | LEAD | COLLABORATING
1 | ECONOMIC DEVELOPMENT | AGRICULTURE DEVELOPMENT | Re-vegetate degraded land with Cashew at Pudua | Pudua |  |  |  |  | 420770.2 | * |  | DA | GPSNP II
2 | INFRASTRUCTURE DELIVERY AND MANAGEMENT | INFRASTRUCTURE DEVELOPMENT | Rehabilitate Small Earth Dam at Sakpe | Sakpe |  |  |  |  | 586072.89 | * |  | DA | GPSNP II/GIDA
3 |  |  | Rehabilitate Small Earth Dam at Lungni | Lungni |  |  |  |  | 586072.89 | * |  | DA | GPSNP II/GIDA
4 |  |  | Rehabilitate Kotoya-Wajuldo-Madado feeder road | Kotoya-Wajuldo-Madado |  |  |  |  | 560641.8 | * |  | DA | GPSNP II/DFR
5 |  |  | Construct a Drain wall at Wulensi Small Earth Dam | Wulensi |  |  |  |  | 289345.78 | * |  | DA | GPSNP II/GIDA
GRAND TOTAL (GH₵) | [8 empty] | 2442903.56